## Agile Plan
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
M1 | M1 | US-M1.1 | Research defect analysis, RAG, embeddings, semantic similarity, vector search, and historical bug datasets. | Must Have | None | Team | Completed
M1 | M1 | US-M1.2 | Design system architecture, agent responsibilities, orchestration flow, and data schemas. | Must Have | US-M1.1 | Team | Completed
M1 | M1 | US-M1.3 | Develop bug submission module with text input and file upload support. | Must Have | US-M1.2 | Team | Completed
M1 | M1 | US-M1.4 | Build historical defect knowledge base with cleaning, chunking, embeddings, and FAISS indexing. | Must Have | US-M1.1 | Team | Completed
M2 | M2 | US-M2.1 | Build Triage Agent for severity, priority, affected component, confidence, and reasoning. | Must Have | US-M1 | Team | Completed
M2 | M2 | US-M2.2 | Build Log Analysis Agent for exception type, failure point, code path, and structured output. | Must Have | US-M1 | Team | Completed
M2 | M2 | US-M2.3 | Implement multi-agent orchestration for Triage and Log Analysis. | Must Have | US-M2.1, US-M2.2 | Team | Completed
M2 | M2 | US-M2.4 | Validate agents using varied bug reports and error-log scenarios. | Must Have | US-M2.3 | Team | Completed
M3 | M3 | US-M3.1 | Build Root Cause Agent using RAG retrieval over historical defects. | Must Have | US-M1.4, US-M2.3 | Team | Completed
M3 | M3 | US-M3.2 | Build Duplicate Detection Agent using semantic similarity. | Must Have | US-M1.4, US-M2.3 | Team | Completed
M3 | M3 | US-M3.3 | Build Remediation Agent for grounded fix recommendations. | Must Have | US-M3.1, US-M3.2 | Team | Completed
M3 | M3 | US-M3.4 | Display structured findings in the frontend interface. | Must Have | US-M3.1, US-M3.2, US-M3.3 | Team | Completed